## Sayfa1
TASK DEFINITION | STATUS | START DATE | FINISH DATE | WEEKS
|  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY
|  |  |  | 1.WEEK | 2.WEEK | 3.WEEK | 4.WEEK | 1.WEEK | 2.WEEK | 3.WEEK | 4.WEEK | 1.WEEK | 2.WEEK | 3.WEEK | 4.WEEK | 1.WEEK | 2.WEEK | 3.WEEK | 4.WEEK
DOCUMENTS | In progress | 26-OCT-21 | 25-OCT-22
Project Proposel Form | Complete | 23-OCT-21 | 5-NOV-21
Project Selection Form | Complete | 24-OCT-21 | 5-NOV-21
GitHub Repository | Complete | 28-OCT-21 | 5-NOV-21
Project Work Plan | Complete | 7-Nov-21 | 12-NOV-21
Literature Review | Complete | 25-OCT-21 | 12-NOV-21
Sofware Requirements Specification (SRS) | Not started | 12-NOV-21 | 10-DEC-21
Project Webpage | Not started | 11-DEC-21 | 17-DEC-21
Software Design Description (SDD) | Not started | 18-DEC-21 | 31-DEC-21
Project Report / Project Tracking Form | Not started | 1-JAN-22 | 7-JAN-22
Presentation | Not started | 5-JAN-22 | 23-JAN-22